## Sheet1
phase | check | evidence_required | owner | status | remarks
FAT | Approved drawings available | Signed drawing list | Vendor
FAT | BOM/makes match approved offer | BOM verification sheet | Joint
FAT | Visual workmanship check | Inspection note | Joint
FAT | Hoist no-load operation | Functional test record | Joint
FAT | CT/LT no-load operation | Functional test record | Joint
FAT | Brake operation check | Brake test record | Joint
FAT | Limit switch operation | Limit switch test record | Joint
FAT | Emergency stop operation | E-stop test record | Joint
FAT | Overload protection check | Test/simulation record | Joint
FAT | Load trial as agreed | Load test certificate | Joint
FAT | FAT punch list closed | Signed punch list | Joint
SAT | Site installation complete | Installation checklist | Joint
SAT | Runway/rail readiness checked | Site readiness note | Buyer/Vendor
SAT | Electrical installation complete | Electrical checklist | Joint
SAT | No-load site operation | SAT functional record | Joint
SAT | Rated load site trial | SAT load test record | Joint
SAT | Safety devices tested at site | Safety test record | Joint
SAT | Operator training completed | Training record | Vendor
SAT | Maintenance orientation completed | Training record | Vendor
SAT | Final snag list closed | Signed closure sheet | Joint
SAT | Final acceptance signed | Acceptance certificate | Buyer