## Sheet1
signal | what_it_looks_like | hidden_risk | buyer_action
Very low price with thin detail | Quote is shortest and cheapest but vague | Scope gaps and claims later | Request clause-by-clause inclusion list
No clear duty basis | Duty class missing or generic | Undersized components | Force explicit duty and cycle basis
Ambiguous exclusions | Many "not in scope" lines without detail | Cost blowouts post-order | Normalize exclusions in comparison sheet
No acceptance detail | FAT/SAT responsibilities undefined | Dispute at dispatch or site | Attach FAT/SAT checklist to PO
Overpromised lead time | Timeline much faster than peers without basis | Delays and penalty conflict | Request milestone plan and constraints
Weak warranty terms | Narrow warranty and many exceptions | Repair costs shifted to buyer | Clarify warranty matrix before PO
No reference depth | References are generic/unverifiable | Trust risk hidden | Run reference call script with 2 live users
Poor response quality | Delayed or unclear technical replies | Future support risk | Track response SLA before selection